## Comm Mgt Plan Template
Communications plan template for project: VitalEdge — GOQii Corporate Wellness Deployment, Meridian Logistics
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Weekly project status meeting | Deval Shah — PM | GOQii delivery team (Kavya, Dev, Sneha, Anil) | Every Tuesday 10:00–10:45 AM, continuous | MS Teams video call | Review sprint progress, open risks, deliverable status, blockers
Bi-weekly sponsor update | Deval Shah — PM | Ms. Priya Nair (Sponsor) + Mr. Arjun Mehta | Every 2 weeks, Monday 11:00–11:30 AM, continuous | MS Teams / in-person at Meridian HQ | Update sponsor on schedule, budget, risks; review change requests
Weekly project status report | Deval Shah — PM | All key stakeholders | Weekly, due Friday by 5:00 PM, continuous | Email + shared Google Drive folder | Written summary of project health — schedule, budget variance, risks, next-week plan
Change Control Board (CCB) meeting | Deval Shah — PM | Sponsor + HR Program Lead + Tech Lead | Monthly, last Monday 10:00–10:30 AM, continuous | MS Teams | Review, approve, or reject formal change requests
Sprint review and app demo | Ms. Kavya Iyer | GOQii team + Mr. Rohit Sinha (Client IT) | End of each 2-week sprint, Friday 3:00 PM | MS Teams screen share | Demo completed app configuration; obtain client IT sign-off per sprint
Device distribution coordination | Mr. Dev Anand | 5 Site Coordinators (Meridian) | 29 Sep 2026, 9:00 AM (one-time) | Email + WhatsApp group | Confirm per-site delivery schedules, contacts, packaging logistics
Employee onboarding announcement | Mr. Arjun Mehta (Client HR) | All 5,000 Meridian employees | 25 Oct 2026 (one-time) | Company-wide email + intranet post | Announce platform launch, enrollment steps, app download, Corporate Challenge dates
Project close-out presentation | Deval Shah — PM | Ms. Priya Nair + full GOQii delivery team | 28 Jan 2027 (one-time) | In-person at Meridian HQ | Present final engagement results vs targets, lessons learned, platform handover