## Template
High-Level Budget: Resource Breakdown Structure Project Name: VitalEdge — GOQii Corporate Wellness Deployment, Meridian Logistics Date: 16th June, 2026
WBS # | Work Package | Int. Personnel | Ext. Personnel | Venue | Materials | Supplies | Equipment | Comments | Total
1.1.1 | Develop project charter | ₹18,000 | — | — | — | — | — | PM time, 3 days | ₹18,000
1.1.2 | Identify stakeholders | ₹12,000 | — | — | — | — | — | PM time, 2 days | ₹12,000
1.1.3 | Conduct project kickoff | ₹20,000 | — | ₹20,000 | — | — | — | Venue + team time | ₹40,000
1.1.4 | Obtain sponsor approval | ₹8,000 | — | — | — | — | — | PM time | ₹8,000
2.1.1–2.1.5 | Project planning docs | ₹95,000 | — | — | — | — | — | All 5 planning artifacts | ₹95,000
3.1.1–3.1.3 | Device logistics & delivery | ₹25,000 | ₹2,00,000 | — | ₹50,000 | — | — | Coordination + courier only | ₹2,75,000
4.1.1–4.1.3 | App configuration (3 Sprints) | ₹6,00,000 | — | — | — | — | — | 2 tech leads × 30 days each | ₹6,00,000
4.1.4 | User acceptance testing | ₹50,000 | ₹1,00,000 | — | — | — | — | Internal + external QA | ₹1,50,000
5.1.1 | Employee training | ₹1,00,000 | — | ₹50,000 | ₹75,000 | — | — | 5 site sessions | ₹2,25,000
5.1.2 | Enrollment campaign | ₹50,000 | — | — | ₹50,000 | ₹25,000 | — | Comms materials | ₹1,25,000
5.1.3 | Launch Corporate Challenge | ₹50,000 | — | — | — | ₹2,00,000 | — | Prizes and rewards | ₹2,50,000
6.1.1–6.1.3 | Monitor & control | ₹1,80,000 | — | — | — | — | — | PM + Analyst, 6 weeks | ₹1,80,000
7.1.1–7.1.3 | Project close-out | ₹95,000 | — | — | — | — | — | Report, handover, retro | ₹95,000
TOTAL COSTS | [8 empty] | ₹20,73,000
Contingency requirements (10%) | [8 empty] | ₹2,07,300
Total with Contingency | [8 empty] | ₹22,80,300
Note: Update cost categories to reflect actual project requirements