Overview:

The Project Charter is the first document created in the Initiation phase. It answers the “what,” “why,” and “who” of the project. The project sponsor must approve the project charter before formal planning can begin.

The Project Charter is often developed based on information provided in a business case, Statement of Work (SOW), or agreement such as a contract, Memorandum of Understanding (MOU), Service Level Agreement (SLA), and so on.

Use this template to create your Project Charter.

Section I: General Project Charter Information

| Charter Item | Comments |
| --- | --- |
| Project name | VitalEdge — AI-Powered Corporate Wellness Platform Deployment for Meridian Logistics Pvt Ltd |
| Project goal | Deploy a fully operational AI-powered employee wellness ecosystem — including smart wearables, a wellness mobile app, AI + human health coaching, and an HR analytics dashboard — to all 5,000 employees of Meridian Logistics Pvt Ltd within 6 months, achieving ≥60% active enrollment and ≥40% sustained 90-day engagement. |
| Project value proposition and benefits | - Proactive, data-driven prevention of lifestyle diseases through daily health tracking (steps, vitals, sleep, nutrition) - Measurable reduction in employee absenteeism linked to preventable health conditions - Team cohesion and morale boost through a structured inter-team Corporate Challenge - HR analytics dashboard giving Meridian visibility into aggregate workforce health-risk distribution for ongoing benefits design - Long-term reduction in group health insurance premium loading - Employer brand differentiation as a health-first organization |
| Problem or opportunity statement | Meridian Logistics Pvt Ltd is experiencing rising group health insurance premiums driven by increasing lifestyle-disease claims and declining employee physical activity following a shift to hybrid work. Employee engagement scores have dropped, and HR leadership lacks real-time, data-driven visibility into workforce health trends. There is a significant opportunity to deploy a preventive wellness platform that addresses these health risks proactively, reduces downstream insurance costs, and rebuilds team cohesion through structured digital wellness engagement. |
| Project schedule | Phase; Description; Dates. 1; Initiation — Charter, stakeholder register, kickoff; Aug 1–15, 2026. 2; Planning — WBS, budget, quality/comms/risk plans; Aug 16 – Sep 5, 2026. 3; Procurement & Logistics — smart band sourcing, 5-site distribution; Sep 6 – Oct 2, 2026. 4; Platform Configuration (Scrum sprints) — app setup, SSO, HRA, dashboard; Sep 15 – Oct 31, 2026. 5; Onboarding & Launch — employee enrollment, training, Corporate Challenge; Nov 1–30, 2026. 6; Operate & Monitor — engagement tracking, status reports; Dec 1, 2026 – Jan 15, 2027. 7; Close-Out — final report, lessons learned, client handover; Jan 16–31, 2027. |
| Project manager | Deval Shah |
| Approval authority/sponsor | Ms. Priya Nair, VP – Human Resources, Meridian Logistics Pvt Ltd |

Section II: Additional Clarifying Information

| Assumptions or constraints | Assumptions: - Meridian Logistics will provide employee data (names, email IDs, site locations) within 2 weeks of charter sign-off. - A minimum of 70% of employees own a personal smartphone compatible with the wellness app (iOS/Android). - The client IT team will complete SSO integration within 3 weeks of receiving vendor technical documentation. - The Corporate Challenge dates will not conflict with Meridian's business peak period (Q3 freight season). - Senior leadership (C-suite + site managers) will actively encourage participation via internal communications. Constraints: - Total project budget is capped at ₹75,00,000. - Employee onboarding go-live must occur no later than 1 Nov 2026 (contractual milestone). - All employee health data must comply with the Digital Personal Data Protection (DPDP) Act, 2023 and the IT Act, 2000. - Platform enrollment is opt-in only — mandatory participation is not permitted. |
| --- | --- |
| Proposed solution(s) high-level overview | GOQii Technologies Pvt Ltd will deploy its AI-powered corporate wellness ecosystem to Meridian Logistics across five parallel workstreams: - GOQii Smart Band procurement and phased distribution across Meridian's 5 office sites (est. 3,500 units for a projected 70% opt-in rate) - GOQii app configuration — Health Risk Assessment (HRA), vitals/activity/sleep tracking, leaderboards — with client SSO integration - AI + human health coaching activation — personalized daily nudges, certified GOQii coach assignments, expert talk sessions - 30-day GOQii Corporate Challenge to drive initial enrollment and sustain engagement momentum - HR analytics dashboard delivering anonymized, aggregate engagement and health-risk reporting to the Meridian HR team The app configuration workstream will be managed adaptively via Scrum (2-week sprints); hardware/logistics workstreams follow a predictive schedule. |
| Project priorities | - Scope — Full platform functionality (wearable + app + coaching + dashboard) must be delivered as contracted; no scope reduction permissible without sponsor approval. - Schedule — The 1 Nov 2026 employee onboarding milestone is fixed (contractual); any delays require a formal change request. - Cost — Budget adherence within ±5% variance; device unit-cost fluctuations to be flagged immediately. - Quality — App uptime ≥99.5%, data security compliance with DPDP Act 2023, and HRA data accuracy are non-negotiable. |
| Return on Investment (ROI) | - Projected 15–20% reduction in lifestyle-disease-related absenteeism over 12 months post-launch (industry benchmark for AI-driven wellness programs) - Estimated ₹18–22 lakhs annual savings in lost-productivity costs at Meridian (based on preventive wellness ROI benchmarks) - Potential 5–8% reduction in group health insurance premium loading at annual renewal, contingent on 12 months of engagement data - Qualitative benefits: improved employee retention, stronger employer brand, and enhanced HR decision-making capability - Estimated payback period: 14–18 months post-deployment |
| Risks (Potential) | - Low enrollment / adoption risk — employees may not opt in without active manager encouragement; mitigation: mandatory leadership communications + incentive structure - SSO / IT integration delays — client IT team bandwidth constraints may delay app go-live; mitigation: fix integration milestone 6 weeks before launch; escalation path via sponsor - Device logistics / procurement delays — import or customs lead-time overruns for smart bands; mitigation: order devices 8 weeks in advance, maintain a 10% buffer stock - Data privacy & security breach — employee health data is sensitive; mitigation: end-to-end encryption, DPDP Act compliance audit before go-live, data-processing agreement with client - Scope creep — client may request uncontracted modules (e.g., mental health, nutrition) mid-project; mitigation: formal change-request process with cost and schedule impact assessment - Low sustained engagement post-Challenge — participants who enroll may disengage after the challenge month ends; mitigation: AI nudge sequences, monthly mini-challenges, coach check-ins - Budget overrun — device unit costs or licensing fees may escalate; mitigation: fixed-price contracts with vendors, 10% contingency reserve in budget |
| Resources required | Human Resources: - GOQii (delivery team): Project Manager (1), Tech & Integration Lead (2), Logistics Lead (1), Health Coaching Lead (1), Data Analyst (1) - Meridian (client-side): HR Program Lead (1), IT & Security Lead (1), Site Coordinators (5 — one per office site) Technology: - GOQii wellness app (iOS + Android), GOQii AI coaching platform, SSO integration layer, HR analytics dashboard, GOQii Smart Band devices (est. 3,500 units) Financial: - Total budget: ₹75,00,000 — allocated across device procurement (~40%), software licensing (~25%), logistics & distribution (~10%), project management & training (~15%), contingency (~10%) Tools: - Project management: Asana / MS Project - Communication: MS Teams / Slack - Documentation: Google Drive / Confluence - Reporting: Google Data Studio / Power BI (HR dashboard) |