## Quality Mgt Plan Template
Quality management plan for project: VitalEdge — GOQii Corporate Wellness Deployment, Meridian Logistics
Part I: Project objectives (reference project charter)
1) Deploy GOQii wellness platform (app + coaching + HR dashboard) to 5,000 Meridian Logistics employees by 31 January 2027
2) Achieve ≥60% active employee enrollment by 30 November 2026
3) Configure GOQii app — SSO integration, HRA, vitals tracking, and coaching module — across 3 Sprints (Sep 15 – Oct 31, 2026)
4) Maintain GOQii app uptime ≥99.5% throughout onboarding and monitoring phases
5) Launch GOQii Corporate Challenge with ≥40% team participation rate (November 2026)
6) Deliver HR analytics dashboard with real-time engagement and health-risk reporting to Meridian HR team
7) Achieve ≥40% sustained 90-day employee engagement post-challenge by 31 January 2027
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Ms. Deval Shah | Project Manager | X | X
Ms. Kavya Iyer | Tech & Integration Lead / QA Lead | X | X | X | X
Mr. Anil Kapoor | Data Analyst / QC Lead | X | X | X | X
Ms. Sneha Rao | Health Coaching Lead (SME) |  |  | X
Mr. Rohit Sinha | Client IT & Security Lead (SME) |  |  | X | X
Mr. Arjun Mehta | Client HR Program Lead (SME) |  |  | X | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Audit app configuration process via Sprint retrospectives |  |  | Verify app functionality — HRA, vitals, coaching module (UAT sign-off)
Audit SSO integration and DPDP Act data security compliance |  |  | Verify SSO integration and DPDP Act compliance test results
Audit employee onboarding and enrollment process execution |  |  | Verify HR analytics dashboard data accuracy and completeness
Audit post-launch engagement tracking methodology |  |  | Verify enrollment numbers and 30-day participation rate metrics
Verify close-out results against project charter objectives