## Risk Register Template
Project: VitalEdge — GOQii Corporate Wellness Deployment, Meridian Logistics Date: 16th June, 2026
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | High leadership enthusiasm at Meridian | Viral adoption exceeding target | Enrollment surpasses 60%; early renewal opportunity | [Your Name] | O | 3 | -4 | -12 | Enrollment rate exceeds 70% by week 3 of onboarding | Scale coaching capacity; propose renewal SLA to sponsor proactively
2 | Employee distrust of health data privacy | Low opt-in during enrollment campaign | <40% enrollment; program KPIs unmet | Arjun Mehta | T | 4 | 4 | 16 | Enrollment below 30% by end of week 2 | Escalate to sponsor; activate manager cascade comms; issue privacy FAQ
3 | Client IT team bandwidth constraints | SSO integration delayed past Oct 31 | App go-live misses Nov 1 contractual milestone | Rohit Sinha | T | 3 | 5 | 15 | SSO configuration not started by Sep 30 | Escalate via sponsor; prepare manual login fallback; raise schedule change request
4 | Smart band transit or customs delays | Device delivery to sites delayed | Onboarding and challenge launch pushed back | Dev Anand | T | 3 | 4 | 12 | Devices not confirmed shipped by Sep 15 | Activate 10% buffer stock; contact alternate local supplier; adjust onboarding date
5 | Meridian HR requesting additions mid-project | Scope creep — e.g., mental health module | Budget overrun; schedule delay | [Your Name] | T | 4 | 3 | 12 | Informal add-on request received from client HR | Invoke formal change request process; assess cost and schedule impact before any approval
6 | Engagement drop after challenge month ends | <40% sustained 90-day active usage | Program ROI not achieved; renewal risk | Sneha Rao | T | 4 | 3 | 12 | Engagement metrics fall >30% in week 5 post-challenge | Deploy AI nudge sequences; launch monthly mini-challenges; flag to sponsor for incentive refresh
7 | Unauthorized access to employee health data | Data breach or DPDP Act violation | Legal liability; reputational damage; possible project halt | Kavya Iyer | T | 2 | 5 | 10 | Security scan alert or employee complaint received | Invoke incident response plan; freeze data access; notify client IT and legal team immediately
Total Risk Score | [7 empty] | 65 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low