## Template
|  | VitalEdge — GOQii Corporate Wellness Deployment | [5 empty] | Level 1 Project level
Initiate Project+C7:D30 | Plan Project |  | Procure & Distribute Devices | Configure Platform | Onboard & Launch | Monitor & Control | Close Project | Level 2 Phase level
1.1.1 Develop project charter | 2.1.1 Develop WBS & network diagram |  | 3.1.1 Procure smart band devices | 4.1.1 Configure app Sprint 1 — SSO & HRA | 5.1.1 Conduct employee training | 6.1.1 Generate status reports | 7.1.1 Prepare close-out report | Level 3 Work package level
1.1.2 Identify stakeholders | 2.1.2 Develop high-level budget |  | 3.1.2 Coordinate 5-site distribution | 4.1.2 Configure app Sprint 2 — analytics dashboard | 5.1.2 Execute enrollment campaign | 6.1.2 Manage change requests | 7.1.2 Conduct lessons learned
1.1.3 Conduct project kickoff | 2.1.3 Develop quality management plan |  | 3.1.3 Verify device delivery | 4.1.3 Configure app Sprint 3 — coaching module | 5.1.3 Launch GOQii Corporate Challenge | 6.1.3 Track engagement metrics | 7.1.3 Handover platform to client
1.1.4 Obtain sponsor approval | 2.1.4 Develop communications plan |  |  | 4.1.4 Conduct user acceptance testing (UAT)
2.1.5 Develop risk register